## Sheet1
Task | Subtask | Work days | Due
Electronics | Main board schematic | 10 | 2020-06-05 | Ignoring the effect of onboarding and supervising postdoc
| Main board PCB layout | 15 | 2020-06-26
| Verilog and C for input data pipe to labview | 6 | 2020-06-29
| Test and debug | 10 | 2020-07-13
| Regulator and distribution cards, box assembly and wiring | 20 | 2020-08-03
Processing | Postdoc onboard + resurrect calibration work | 30 | 2020-07-15 | With 01-Jun postodc start date, 50% my effort
| Calibration paper | 15 | 2020-08-05
| Real-time pose solution | 40 | 2020-10-01
| High/low pose solution and metal interference experiments | 30 | 2020-11-15
| Metal interference paper | 10 | 2020-12-01
| Move Labview signal processing into C++ | 30 | 2020-02-15
EM interference | Lab testing | 20 |  | Mostly my effort
| EMI paper | 10